## Sheet1
Date | Duration (h) | Timeframe | Topic | Status
Thu, 18-Jan | 8 | 08:00-17:30 | Mock Project - Day 1 - Kick off + Create requirement outline | Started
Fri, 19-Jan | 8 | 08:00-17:30 | Mock Project - Day 2 - Create SRS
Mon, 22-Jan | 8 | 08:00-17:30 | Mock Project - Day 3 - Review and update SRS
Tue, 05-Feb | 8 | 08:00-17:30 | Mock Project - Day 4 - Database Design + Review Database Design
Wed, 06-Feb | 8 | 08:00-17:30 | Mock Project - Day 5 - Create Blackbox Testcase
Thu, 07-Feb | 8 | 08:00-17:30 | Mock Project - Day 6 - Review and update Blackbox TC
Fri, 08-Feb | 8 | 08:00-17:30 | Mock Project - Day 7 - Coding
Mon, 11-Feb | 8 | 08:00-17:30 | Mock Project - Day 8 - Coding
Tue, 12-Feb | 8 | 08:00-17:30 | Mock Project - Day 9 - Coding
Wed, 13-Feb | 8 | 08:00-17:30 | Mock Project - Day 10 - Coding
Thu, 14-Feb | 8 | 08:00-17:30 | Mock Project - Day 11 - Review code + UT
Fri, 15-Feb | 8 | 08:00-17:30 | Mock Project - Day 12 - UT
Mon, 18-Feb | 8 | 08:00-17:30 | Mock Project - Day 13 - IT
Tue, 19-Feb | 8 | 08:00-17:30 | Mock Project - Day 14 - IT + Create Test Report
Wed, 20-Feb | 8 | 08:00-17:30 | Mock Project - Day 15 - Final Report
Thu, 21-Feb | 8 | 08:00-17:30 | Mock Project - Day 16 - Final Report (cont)
Fri, 22-Feb | 8 | 08:00-17:30 | Sum-up and Closing Ceremony
Mon, 25-Feb | 2 | 08:00-10:00 | Class Meeting 3
Mon, 25-Feb | 2 | 10:00-12:00 | TOEIC Test 2
Mon, 25-Feb | 4 | 13:30-17:30 | Re-test session 2 (For ASQL, ATXB)
Tên đề tài: | Hotel Management System
Trần Minh Trung
Nguyễn Anh Hải
Nguyễn Anh Kiệt
Trần Thị Phương Hà
Trần Quốc Khánh